## v.2.3.0
| 2.7.0 |  | UAT Document Satuinbox Web App |  |  |  | Checklist Dev & QA
| 2026-07-13 | Apps Name : | Satuinbox Web App | PM : | Dany Christian |  | General |  | Backend |  | Frontend |  | QA
| Dany Christian | Version : | 2.5.0 | QA Name : | Dany Christian |  | Review and approve all pull requests | TRUE | Database migrations reviewed and tested. | TRUE | Verify cross-browser compatibility. | TRUE | Functional Testing | TRUE
| Dany Christian | Date : | 21 Mei 2026 / 22.00 WIB | TechLead : | Naftal Yunior |  | Ensure all unit tests are passing. | FALSE | Backup existing database. | TRUE | Ensure responsiveness on different devices. | TRUE | Regression Testing | FALSE
| Naftal Yunior | [5 empty] | Ensure all integration | TRUE | Ensure environment variables are | TRUE | Check for accessibility compliance. | TRUE | Performance & Stability | FALSE
[7 empty] | tests are passing | TRUE | properly configured | TRUE | Review and optimize loading times | TRUE | Security Testing | FALSE
|  | FEATURE / BUG |  |  |  |  | Code review completed and approved by team lead | TRUE | Verify endpoint security and authentication mechanisms. | TRUE | Test new UI components in a staging environment | FALSE | UI/UX Validation | TRUE
|  | Feature | Description | Enhancement | Evidence | Test Results | Update documentation (if necessary) | TRUE | Load testing completed and performance verified. | TRUE | Verify integration with backend APIs. | FALSE | API Testing | FALSE
[7 empty] | Ensure proper versioning (Semantic Versioning: MAJOR.MINOR.PATCH) | TRUE | Logging and monitoring set up for new endpoints | TRUE | Ensure error handling and user feedback is clear. | TRUE | Smoke Testing | TRUE
[8 empty] | FALSE | Ensure backward compatibility with existing endpoints | TRUE | Update user-facing documentation (if applicable) | FALSE |  | FALSE
[8 empty] | FALSE | Review API documentation and update if needed. | TRUE |  | FALSE |  | FALSE
[8 empty] | FALSE | Run final smoke tests on the staging environment. | TRUE |  | FALSE |  | FALSE
1 | Whatsapp Web - inconsistency account channel status | Description : | No | https://project.ordo.co.id/wp/2052 |  |  | In testing | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | High
2 | Fix RabbitMQ Ticket Service Restart Issue | Feature: Fix RabbitMQ Ticket Service Restart Issue | Yes | https://project.ordo.co.id/wp/2344 |  |  | In testing | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
3 | Update baileys lib to v7 rc-10 | Update the @whiskeysockets/baileys library to version 7 release candidate 10. | Yes | https://project.ordo.co.id/wp/1820 |  |  | In testing | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
4 | Whatsapp API - conversation created without message | handle issue whatsapp api terkait conversation (WAPI CHANNEL) dengan kondisi tanpa message | No | https://project.ordo.co.id/wp/2227 |  |  | In testing | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
5 | WhatsApp Group Messages - From Certain Participants Are Not Displayed in SatuInbox and Reply Context Is Missing | An anomaly was found in WhatsApp Group conversations where messages from certain participants are successfully delivered and visible in the native WhatsApp application (mobile/web), but those messages do not appear in the SatuInbox Group Co | No | https://project.ordo.co.id/wp/2216 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | High
6 | Analitycs - report offline - Offline Report Status Not Updating on Pagination or Navigation | ### Jam.dev Evidence | No | https://project.ordo.co.id/wp/1708 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
7 | Handle autofill data on mobile ( SALES FORM ) | autofill form : | No | https://project.ordo.co.id/wp/2210 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
8 | Leads - Empty State Information Missing in Existing Contact Tab on Add Prospect | Jamdev : | No | https://project.ordo.co.id/wp/1834 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
9 | Leads - Invalid Validation on Company Phone Number and Email/Company Email Fields in New Contact Form | Jamdev : | No | https://project.ordo.co.id/wp/1823 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
10 | Notification - Incorrect Time Display in Notification Description (Using UTC Instead of Local Time) | Jam.dev Evidence | No | https://project.ordo.co.id/wp/1572 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
11 | Settings-Subs-Payment -Invoice Filters & Export Not Working and Tab State Not Reset After Page Reload | ### Jam.dev Evidence | No | https://project.ordo.co.id/wp/1089 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
12 | Ticket List - KPI Card Counter Not Synced During Real-Time Ticket List Pagination Update | ### Jam.dev Evidence | No | https://project.ordo.co.id/wp/1810 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
13 | Leads - Visit Detail - Decision Section UI Not Matching Design | Jamdev : [https://jam.dev/c/c01e2046-56e8-4831-982b-8c6d4bd0e726](https://jam.dev/c/c01e2046-56e8-4831-982b-8c6d4bd0e726) | No | https://project.ordo.co.id/wp/1625 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Low
14 | Leads - Visit History - Late and Reschedule Badges Not Properly Arranged in Planned Column | Record : | No | https://project.ordo.co.id/wp/1619 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Low
15 | Leads-Add Data-Filter Select - Checkbox Overlaps Text in Lead Contact Filter Selection UI | Jamdev : | No | https://project.ordo.co.id/wp/1814 |  |  | Tested | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Low
16 | Add global search config | add config for global search in organization | Yes | https://project.ordo.co.id/wp/2434 |  |  | Closed | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
17 | Auth - change validation at onboarding (TEMP V2.7.0) | ## QUICK ACT (TEMP V2.7.0) | Yes | https://project.ordo.co.id/wp/2277 |  |  | Closed | User story |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
18 | Broadcast - Broadcast Can Be Sent Successfully Even When Token Balance Is Rp 0 | ### Jam.dev Evidence | No | https://project.ordo.co.id/wp/1207 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
19 | Chatbox Copy Paste from Clipboard Features | Ada kebutuhan untuk Copy Paste Images pada Chat Box (bukan Upload Attachment) | Yes | https://project.ordo.co.id/wp/1757 |  |  | Closed | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
20 | Conversation - add event assignBy data | adding assignBy id, assign type | Yes | https://project.ordo.co.id/wp/2112 |  |  | Closed | User story |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
21 | Create OPEN API Team inbox | create ticket from api need fill member ids and team id, this endpoint shoul provide them response minimal is showing :&nbsp; | Yes | https://project.ordo.co.id/wp/2393 |  |  | Closed | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
22 | File compability - support heic dan heif type file | support heic dan heif type file | No | https://project.ordo.co.id/wp/1959 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
23 | Global search suggestion | # PRODUCT REQUIREMENT DOCUMENT | Yes | https://project.ordo.co.id/wp/2140 |  |  | Closed | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
24 | Improve ticket room- user can reply message from selected bubble | Update Ticket Room: Users can now dynamically select any message bubble within the conversation ticket to be used as the reply reference bubble. | Yes | https://project.ordo.co.id/wp/2209 |  |  | Closed | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
25 | IT Support - Conversation Room Broadcast | Bug Broadcast terkirim 2 kali dalam waktu yang berdekatan atau rentang 2 menit kepada penerima yang sama | No | https://project.ordo.co.id/wp/2128 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
26 | Shift Hour - Change shift hour did not effect member | Description : | No | https://project.ordo.co.id/wp/1975 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
27 | Spintext - dynamic configuration spintext (TEMP 2.7.0) | Quick patch v2.7.0 | Yes | https://project.ordo.co.id/wp/2363 |  |  | Closed | User story |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
28 | Ticket - direct from ticket to conversation result static path URL | Description : | No | https://project.ordo.co.id/wp/2226 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
29 | Whatsapp - message utility ( contact, poll, event ) | ##### UI link : [https://www.figma.com/design/RAAuLaQKUufWMWWEm0kMb9/-V2--Satuinbox-Web-Specs?node-id=11944-107541&amp;t=maM2yZmwk9HFkPSf-1](https://www.figma.com/design/RAAuLaQKUufWMWWEm0kMb9/-V2--Satuinbox-Web-Specs?node-id=11944-107541&t | Yes | https://project.ordo.co.id/wp/2058 |  |  | Closed | Feature |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
30 | conversation - reopen conversation with account channel that already disconnected and deleted, can still be done | used account :&nbsp; | No | https://project.ordo.co.id/wp/1132 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Low
31 | WhatsApp Group Conversation - Support @All Mention | Currently, the WhatsApp Group Mention feature only supports mentioning individual participants. | No | https://project.ordo.co.id/wp/2218 |  |  | Closed | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Low
32 | [Mobile] - Search Autocomplete/Filtering Does Not Return Result for Partial Keyword Match | Jamdev : [https://app.betterbugs.io/session/6a1506f2247a3e53fa31531c](https://app.betterbugs.io/session/6a1506f2247a3e53fa31531c) | No | https://project.ordo.co.id/wp/1940 |  |  | On hold | Bug |  | v2.7.0 | Staging/Prod | SatuInbox | Normal
RollBack Plan

## Sheet5
Feature | Description | Enhancement | Evidence Link
Conversation Event Logs | Tampilkan timeline event conversation (close, reopen, add/remove member, team inbox change, sender number change, SLA, screenshot) di Conversation Detail secara chronological | Panel "Conversation Events" collapsible dengan 5 event terbaru + "See all" untuk full list; event tercatat dengan actor, timestamp, dan payload | OpenProject #674
Export Ticket Image GENERAL - Public Link | Export image custom field di XLSX sebagai non-expiring preview link (bukan S3 URL langsung). Link bisa di-revoke | Token-based preview URL dengan high entropy, short-lived presigned URL (TTL ≤60s), revoke API idempotent, retry policy pada export job | OpenProject #776
Dashboard > Member Analytics: Self Filtered View Based on RBAC | Member dengan assigned_only analytics scope hanya bisa lihat statistik sendiri. Supervisor/Admin bisa filter Me/Team Inbox/Agent | Filter "Saya" otomatis untuk agent, chip locked tidak bisa dihapus, backend enforce scope, query tampering blocked | OpenProject #1291
Contact Detail - Conversation History Scroll & Click | Conversation history di contact details tidak bisa di-scroll dan tidak ada redirect saat diklik | Fix scrollable conversation history list; click redirect ke conversation room (jika user punya permission) | BetterBugs Session
Conversation Count Mismatch & API Data Inconsistency | Counter "Your Inbox (Open)" tidak match dengan list conversation yang ditampilkan. API total=6 tapi UI render 5 | Fix konsistensi counter UI, displayed list, dan backend API total; alignment filtering logic frontend-backend | BetterBugs Session
Notification - Mark as Read Function | Fitur mark as read pada notifikasi | Mark as read per item, mark as read all, button direct ke item (conversation/ticket) | OpenProject #1681
Analytics - Offline Report: Deleted Agent Validation | Agent yang sudah dihapus masih bisa digunakan di offline report request | Validasi agent existence sebelum submission; error message jika agent sudah tidak valid | BetterBugs Session
Analytics - Offline Report RBAC Visibility | Supervisor bisa melihat report milik supervisor lain (seharusnya tidak) | RBAC fix: Supervisor hanya lihat report sendiri + report Admin; Admin tetap lihat semua | BetterBugs Session
Conversation - Star & Spam Filter & Counter | Starred tab tidak menampilkan data (counter=0). Spam tab counter=0 padahal data ada | Fix filtering logic starred conversations; sinkronisasi counter dengan filtered data | BetterBugs Session
Ticket - Responsive Ticket Page | Ticket list tidak accessible pada viewport 1366x633 | Fix responsive layout ticket page untuk viewport kecil | Jam.dev Evidence
Leads - Contact Filter Limit Parameter | Contact filter di Leads → Add Data masih pakai limit=10 sehingga data tidak tampil semua | Remove limit parameter saat filter selection; load full dataset berdasarkan filter yang dipilih | BetterBugs Session
Contact - Add Contact Channel Dropdown Scroll | Channel dropdown di form Add Contact tidak bisa di-scroll | Fix dropdown scrollable saat option list melebihi visible area | BetterBugs Session
[Mobile] - Outbound Chat Auto Assign | Saat kirim pesan dari unassigned chat di mobile, user tidak otomatis jadi assignee | Fix auto-assign current user saat outbound message dari unassigned chat | BetterBugs Session
Ticket Improvement - Assignee & Closed By | Saat create ticket assignee harus user login (bisa diganti). Closed ticket hanya oleh creator/supervisor | Auto-fill assignee dengan user login saat create ticket; restrict closed action ke creator atau supervisor saja | Jam.dev Evidence 1 / Jam.dev Evidence 2
[Mobile] - Unassigned Chat First Message Not Sent | Pesan pertama dari unassigned chat di mobile tidak terkirim, conversation otomatis pindah ke "Pesan Anda" | Fix first message send flow dari unassigned chat; prevent premature auto-move ke "Pesan Anda" | OpenProject #1905